## Slide 1: End of Study

## Slide 2: Goal
508 outcomes
Current projection: May 2018
Challenges and considerations
  We need 508 outcomes, no fewer
  Impossible to stop at exactly 508
  Consideration of UNCOs – do people stay on pills?
  *Plan was developed with the above in mind

## Slide 3: End of Study Process Initiation
Procedures will begin prior to 508 events being reached
*
508 events reached
(estimated)
Announcement to start EOS procedures
Data lock
-2 months
Complete EOS visits
+3 months
+5 months
Completion of EOS visits and UNCOs (as needed)
Data cleaning and UNCOs

## Slide 4: How is this different?
Previous protocol version had a dedicated end of study visit
New protocol uses the next scheduled visit as the end of study – easier because study visits proceed as usual

## Slide 5: What is an EOS visit?
An EOS visit is the participants next scheduled visit
  Will mostly occur as scheduled (a few exceptions)
Participants will be given a new bottle of study pills* and asked to continue taking pills until contacted by site
UNCO will be done as needed
After visit , EOS letter given
  Plan going forward – when glycemia results and study pill assignment will be released and when study results will be available

## Slide 6: *Exceptions to Standard EOS Visit
Previously met diabetes outcome
  Pills will not be given
  No additional visits will be required
Previously discontinued study pills
  Pills will not be given
  UNCO visit may still be necessary depending on lab results

## Slide 7: No UNCO Visit Required
Site staff will call participant post-visit to let them know that all results were negative
Study pills collected
Letter sent to participant and PCP

## Slide 8: EOS UNCO Visit
UNCO visit is conducted the same as it has been throughout the study
  Participant stays on study pills
Study pills will be collected and no new bottle dispensed
After visit, letter sent to participant and PCP

## Slide 9: End of Study Visit
Review results (see MOP18, MOP14)
Is UNCO visit needed?
Annual or semi-annual visit
Collect study pills and dispense new bottle
Discuss method of returning study pills (provide pre-paid envelope, if necessary)
UNCO visit
Collect study pills
Ask participant to continue study pills
Schedule UNCO visit
Yes
No
Participant has met diabetes outcome?
Annual (no OGTT) or semi-annual visit
Collect study pills
No
Yes
Send post-visit letter to participant and PCP
Recover study pills
(In-person or mailed using pre-paid envelope)

## Slide 10: End of Study Visit – Study Pills Discontinued
Review results (see MOP18, MOP14)
Is UNCO visit needed?
Annual or semi-annual visit
Collect study pills and dispense new bottle
Discuss method of returning study pills (provide pre-paid envelope, if necessary)
UNCO visit
Collect study pills
Ask participant to continue study pills
Schedule UNCO visit
Yes
No
Participant has met diabetes outcome?
Annual (no OGTT) or semi-annual visit
Collect study pills
No
Yes
Send post-visit letter to participant and PCP
Recover study pills
(In-person or mailed using pre-paid envelope)

## Slide 11: Example: Alfred
M36 Visit
Announcement to begin EOS procedures
M39 Contact
M42 Visit = EOS visit
508 outcomes
(projected)
Complete EOS
Data lock
UNCO Visit
May 2018
Apr 2018
Mar 2018
Feb 2018
Jan 2018
Jun 2018
Jul 2018
Aug 2018
Sep 2018
Oct 2018
On study pills
Has not met diabetes outcome

## Slide 12: Example: Bruce
M42 Visit
Announcement to begin EOS procedures
M45
Contact
M48 Visit = EOS visit
508 outcomes
(projected)
Complete EOS
Data lock
M48 Target
May 2018
Apr 2018
Mar 2018
Feb 2018
Jan 2018
Jun 2018
Jul 2018
Aug 2018
Sep 2018
Oct 2018
M45 Target
Complete EOS
M48 Target
On study pills
Has not met diabetes outcome

## Slide 13: Post-Study Communication
Participant’s results and group assignment cannot be unblinded until primary outcome has been analyzed and manuscript published
A process will be developed to make sure sending these results out is as easy and low-effort as possible
Summary of results will be included with a reference to the manuscript

## Slide 14: MOP Reference
MOP Section 20: End of Study
Detailed instructions
Letter templates for IRB submission
MOP Section 13: Source Documents
Updated – released at EOS announcement